APPLICATION OF LEAN SUPPLY CHAIN CONCEPTS TO A VERTICALLY-INTEGRATED COMPANY: A CASE STUDY

Nadia G. Akel, Iris D. Tommelein, J.C. Boyers

# Abstract

This study focuses on the application of lean supply chain concepts to a vertically-integrated pre-engineered metal building manufacturing company, Butler Manufacturing, in order to help streamline    its order processes. Specifically, the study discusses illustrates the application of value-stream mapping tools to reduce cycle time for the Butler order process. While value stream mapping tools have been used before in construction cases, this paper presents an analysis for a different context (that of a Butler order) as well as a different industry sector. In addition to the value-stream analysis, the paper discusses specific supply chain metrics that are used in this case study to analyze order data that cover Butler’s in-house supply chain from order-taking to shipment. The overall aim of this research is to assist Butler in determining to what extent vertical integration is appropriate for them in order to entrench itself in the pre-engineered metal building market.

# KEY WORDS

Vertical integration, value stream mapping, supply chain management, lean production, pre-engineered metal building systems, Butler Manufacturing, change orders.

# introduction

This research investigates lean supply chain practices at Butler. Butler engineers, designs, manufactures, and erects pre-engineered metal buildings and components both domestically and internationally. The Butler supply chain comprises supply in-house, reaching from one functional division (e.g., design) into another (e.g., fabrication). It also reaches outside of the organization, upstream to third-party vendors and downstream to independent contractors. The company’s vertically integrated nature creates a unique opportunity with regards to improved supply-chain practices in the otherwise fragmented AEC industry. For instance, Butler is able to fabricate all primary and secondary structural steel components of a 100,000 ft2 building in a 13-day time window after release of detail drawings.

Butler offers a variety of pre-engineered metal buildings, ranging from more standardized, modularized designs to 100% custom designs. Standardization and modularization create unique opportunities for efficient supply chain practices. The researchers, jointly with their Butler sponsor, therefore decided to study these most standardized products, which Butler calls the A-cell buildings, particularly since A-cell buildings comprise 60% of Butler’s orders. A-cell buildings are based on a kind of parametric design that allows for customization while also considering efficiency and cost-effectiveness of fabrication. While Butler’s product takes advantage of Butler’s in-house design and fabrication capabilities, information and materials do not flow as smoothly as they could across internal organizational boundaries. As a result, the product lead time from order taking to materials delivery on site is larger than it could be, when considerations for continuous flow are taken into account.

The purpose of this case study is therefore to explore the benefits of applying lean production and supply chain management practices to Butler. The study focuses on Butler’s supply chain practices with regards to the design and fabrication of its A-cell buildings in order to investigate the possibilities of achieving closer alignment between Butler’s design/manufacturing arm and its construction arm. This entails identifying internal hand-offs and buffers, and then creating flow and implementing other lean practices in Butler and its subsidiaries. Alignment may be achieved by implementing lean production principles not only within but also across organizational boundaries.

# BUTLER BACKGROUND

Butler performs the design of its pre-engineered metal buildings in-house because the required structural engineering knowledge in cold-formed steel design is neither widely taught nor readily available. In fact, Butler has engineering design offices in each of its six U.S. manufacturing facilities to serve regional markets. In recent years, the pre-engineered metal building industry has moved from modular, fully standardized buildings to custom buildings. Butler has followed that move but many of its processes rely on parametric designs so that the company can still take advantage of modularity in its order-taking, materials-procurement, and fabrication processes.

Butler brings its building systems’ products to market through various agreements with general contractors. It sells its materials predominantly through two construction channels—Butler Builders, a network of local, independent general contractors authorized to sell and erect Butler Buildings, and Butler Construction (BUCON), Butler’s own construction arm. Butler’s two main types of distributors serve different construction markets and therefore do not compete with each other.  Akel et al. (2001) describes Butler’s organization and distributor network in further detail. Tommelein et. al. (2003) describes Butler’s supply chain process in greater detail than this paper.

# Butler Order Data

While this case study focuses on Butler as a national corporation, most of the data was obtained in working with personnel at their Visalia, CA plant. This choice was driven largely by proximity of this plant to U.C. Berkeley (4.5 hour drive each way) but also by the fact that personnel at this plant already took significant effort in mapping their processes and implementing lean production practices. Such practices consistently lead to improved supply chain performance.

The data for the value stream mapping analysis are based on 21 actual Butler Visalia Pronto orders. These are all the Butler Pronto orders for a single, larger-sized Butler Builder placed in 2001. These 21 orders correspond to 18 projects in the California Central Valley. Therefore, for the most part, each of these Butler Builder projects corresponds to one Butler order. From all the data, there was one Builder project that was broken down into three Butler orders.

# METRICS

At its production facilities, Butler uses three main metrics: value added time (VAT), manufacturing cycle time (or throughput time), and manufacturing lead time. These terms are defined below along with other supply chain metrics that are used in this case study to analyze order data that cover Butler’s in-house supply chain from order-taking to shipment. The definitions used here are from Hopp and Spearman (2000), the Supply Chain Operations Reference (SCOR) Model Metrics (SCOR 2000), and the Lean Construction Institute (LCI 2002).

Cycle Time [unit of time]: The time for a product to go from the beginning to end of a production process; i.e., the time the product spends as work-in-process (Hopp96, Lean02). Cycle time includes three components: (1) value-added time, (2) setup time, and (3) wait time; these are defined next. Butler refers to cycle time as the manufacturing lead time (MLT). Butler also uses manufacturing cycle time (MCT) to denote VAT and Setup Time.

Cycle Time  = VAT + Setup Time + Wait Time = MLT = MCT + Wait Time

Value-Added Time (VAT) [unit of time]: The time necessary to actively work (design, engineer, fabricate, etc.) on an item (such as a project design, a beam, a clip, etc.). The time spent to perform a conversion task. VAT does not include setup or wait time.

Setup Time [unit of time]: Time it takes to change over and ready a machine or production unit to start the next task or operation.

Queue Time [unit of time]: Wait time. The time that an item is sitting around waiting in a queue.

Throughput (or Throughput Rate) [unit of quantity/unit of time]:  The average output rate of a production process (machine, workstation, line, plant) per unit time (e.g., parts per hour) (Hopp96, Lean01).  The limit on the throughput is the capacity.

Capacity [unit of quantity/unit of time]: an upper limit on the throughput of a production process (Hopp and Spearman 2000 p. 216).

Schedule Plan Stability: The number of times the scheduled delivery date changed after it was fixed once it appeared within the critical time fence. The critical time fence defines the moment in time after which changes to the order become significantly more expensive to accommodate than they were, had they been made earlier (e.g., materials that were obtained and partially completed may become obsolete). It is the boundary between flexible and fixed capacity SCOR (2000).

Delivery Performance to Scheduled Commit Date: The percentage of orders that are fulfilled on or before the original scheduled or committed date (SCOR 2000).

# ANALYSIS AND OBSERVATIONS

## Value Stream Analysis: Butler Order Process

Value stream mapping is used by the Toyota Production System practitioners to depict current and future, or “ideal,” states in the process of developing implementation plans to install lean systems. A value stream analysis of the Butler order process was performed in order to assess information and material flow, to identify the sources of waste, and to help visualize the entire order process. Per Rother and Shook (1998), Brunt (2000), Rother and Harris (2001), and Jones and Womack (2002), a value stream consists of all the actions (both value and non-value added) currently required to bring a product through the main flows essential to every product: (1) the production flow from raw material into the arms of the customers, and (2) the design flow from concept to launch.

### Value Stream Map: Current-State

To create the value stream map for Butler’s order process (Figure 1), an order was followed from the point at which an order is placed by a Builder to the point at which the Butler product is shipped to the construction site. The value-adding steps are shown as rectangles, and the hand-offs with delays are shown as triangles.

Figure 1: Value Stream Map of Butler Visalia’s Order Process. Circled numbers correspond to the process lead time descriptions in Table 2. (adapted from Tommelein 2003)

The value stream map in Figure 1 shows activity durations (in total man-hours [mh] of work content) and lead time estimates provided by Butler personnel. The “average total actual time in system”estimated average lead time of a Butler order from the point the order is assigned to the actual ship date. In contrast to Figure 1, Figures 2-6 show planned and actual lead times from the Butler order data. Table 1 summarizes relevant statistical calculations for these figures. Note that original planned dates are the dates set prior to change orders, while revised planned dates correspond to planned dates that have been amended via change order.

An interesting observation is that the estimates provided by Butler personnel (in Figure 1) are relatively close to the mode (most-likely) values calculated from the Butler order data. This is primarily due to the fact that the distributions are all highly-skewed (Figures 2-6). For example, the mode duration for the planned design activity is only 1 day, which is very close to Butler Visalia’s estimate of 6 man-hours (4 hours for engineering design and 2 hours for design check). However, the average duration is much larger at 6.7 calendar days since it accounts for the outliers. Due to the skewed nature of these lead time distributions, Butler personnel properly used mode values as these do not account for the rare case of having an unusually long duration.

| Figure 2 | Figure 3 |
| --- | --- |

| Figure 4 | Figure 5 |
| --- | --- |

Figure 6

The time required to obtain permits depends on the location and the number of projects that that city is processing—hence, the 2-week to 2-year range provided by Butler personnel in Figure 1 . In Los Angeles, for example, permits take roughly 9 months to procure. In contrast, permits can be obtained in about 3 weeks in a small municipality such as Visalia. The Butler order data analyzed had a mode of 1 week and an average of 12 weeks.

Table 1: Statistical calculations for Butler order process times

* Circled numbers to the right of table correspond to those in Figure 1.

By comparing the data estimated by Butler personnel in the value stream map in Figure 1 to the actual order data in Table 1, performance metrics can be assessed.  The total VAT in Figure 1 was shown to be roughly 1.28 weeks. This is 1.6 to 12.8% of the total estimated lead time (LT). When compared to actual order data, the VAT/LT is roughly 5.6% as shown in Table 2.

To compare the value-added time to other sectors of the construction industry, Arbulu and Tommelein (2002) showed that VAT/LT is on the order of 3.5 to 4% for the power plant pipe support supply chain. Similarly, Elfving et. al. (2002) indicated that VAT is less than 10% of total LT in power distribution supply chains and that it can be radically improved (Elfving 2003). Hopp and Spearman (2000, p. 327) identify that “In most production systems, actual process and move times are a small fraction (5-10 percent) of total cycle time.”  Anecdotal evidence in lean construction shows that VAT/LT is on the order of 1/20 (5%) for design and 1/10 – 3/10 (10-30%) for fabrication but those are merely rule of thumbs.

Table 2: Percentage of Value-Added Time for overall Butler order process times (adapted from Tommelein 2003)

From the anecdotal evidence, it seems that Butler’s value stream can be appreciably streamlined since its VAT/LT ratio is on the low end at 5.6%, especially when considering that this number is for their standard parametric designs. Improvements can be made by reducing queue time and setup times in the overall system. Increasing VAT up to 20% of LT has been done in manufacturing and is a reasonable aim. In fact, one of the aims of supply chain management should be to increase the value of this ratio to 20% if not more (Tommelein 2002).

Table 2 shows value-added times to lead time ratios computed using actual plant data. These include three sets of values, corresponding to (1) the original plan, (2) the revised plan, and (3) actual execution. Not surprisingly, the VAT/LT ratio is higher when considered planned times as opposed to actual times because planners tend to be optimistic and eventually schedules slip.

## Manufacturing Lead Times

Figure 7 illustrates the value-added time (shown in green), setup time (yellow), and queue time (red) for various components fabricated at the Visalia plant. The total manufacturing lead time is comprised of the green, yellow, and red bars shown in the figure. Note that the bars shown are not drawn to scale.

As encountered in the previous section, VAT is a very small percentage of the total manufacturing lead time for all the components, with exception of the secondaries. The VAT/LT ratio varies greatly for different components. Primaries have an average ratio of 0.5% while wall roof panels have a ratio of 0.02%! In contrast, secondaries are more efficiently produced with a ratio of 25-50%.

Figure 7: Manufacturing lead time information for material fabricated at Butler Visalia

Figure 7 also shows the weekly plant production capacity for each component. For example, the Visalia plant can fabricate 800 primary components weekly. To get an appreciation of the production capacity of the various components, Figure 8 shows a material take-off for a small Butler building with a 60’ by 1000’ footprint. For purposes of comparison, most Butler Builder buildings are on the order of 50,000 to 100,000 square feet (Akel 2001).

The Visalia plant typically processes 25-30 orders per week. Sometimes, the Visalia plant will handle more or less, depending on customer demand. Typically, there are 8-9 jobs ongoing at any one time. The Visalia plant itself has enough capacity to manufacture 700-800 frames pieces per week. For comparison purposes, a 100,000 square-foot building consists of approximately 200 frame pieces.

The basic elements of any pre-engineered metal building system are constant: primary rigid frames, secondary members (wall girts and roof purlins), cladding and bracing (Shoemaker 1999). The secondary members are usually cold-formed into C and Z shapes. The primary frames are designed using welded plate members instead of the hot-rolled sections used in conventional steel design. This practice permits the use of tapered beam sections. By varying the web depth and flange size over the length of a member, pre-engineered metal manufacturers can produce designs that are more cost effective than their conventional steel counterparts.

Figure 8: A widespan Butler building with a 60’ x 100’ footprint. [Nadia to do actual takeoff]

## Batching

The hand-off from design to fabrication—governed by Butler’s proprietary, computer-aided design system, named Pronto—is still traditional and batch-oriented. Opportunities for process improvement are to be investigated in this area.

The batching rules in Figure 2 reveal the hand-offs for a particular Pronto project. First, unless a project has completely regular plan and elevation views—i.e., a rectangular-shaped building with no mezzanine—it is broken down into multiple ‘regular-shaped’ orders for Pronto design purposes. Second, a Butler order is then broken down into manifests—one for each fabrication location and outside suppliers. Third, an internal Butler manifest is then broken into phases for production scheduling purposes. Finally, once the fabrication is completed and Butler receives the supplies from its suppliers, the order is then reassembled and again broken down into transportation manifests. Such batch-oriented hand-offs (Figure 2) cause matching problems, thereby rendering the order process less efficient.

Figure 9: Batch-Oriented Hand-Offs for Butler Builder projects

## Change Order Analysis: Schedule Plan Stability

Of the 21 Butler Pronto orders analyzed in this case study, 11 (52%) had change orders. The number of change orders per Butler order ranged from 0 to 6, with the average being 1.19. All change orders, with the exception of one, were for postponing planned ship dates and/or engineering release dates. While the percentage of projects with change orders seems high, changes relating to planned ship dates are normal and relatively common in the construction industry. Assuming that all the planned ship date changes were made within the critical time fence, the Schedule Plan Stability for the Butler orders analyzed was therefore 1.14. Note that the Schedule Plan Stability is less than the number of change orders per Butler order of 1.19. This is due to the fact that some change orders did not affect the time fence.

Figure 9 compares and contrasts the total delivery time of orders that did not have change orders (‘A’) with those that did (‘B’). The dotted red bars show the duration of permitting and detail engineering. Since detail engineering has a value added time of 16 mh while the bars are on the order of 8-15 weeks, we can conclude that the bars primarily represent permitting delays. Several observations can be made about the data. However, please note that our observations are speculative and are based on a small number of data points (21).

Permitting has a long lead time that can be reduced significantly: Most striking is the large variation in duration needed for permitting, in particular because the projects analyzed are all built in the same geographic area. The planned time required to get a permit is about 15.5 weeks for orders without changes, and slightly over half of that, 8 weeks, for orders with changes. Barring regional and design differences, we speculate that orders with changes are ‘on the fast track’ and require permit expediting, which may be done either for a fee, or simply by more active expediting, or the like.

Figure 10: Butler orders with and without change orders

Figure 10-5 may give the impression that permitting drives the start of engineering detailing and of fabrication further downstream, but the drawing does not show other supply chains feeding into this one, such as the supply of materials. A reduction in the time for permitting and thus between design and fabrication, may constrain the time available for materials procurement, mobilization, and stocking. Performance improvements for those tasks are then needed in order to make it possible for fabrication to start earlier.

It is difficult to jump start the delivery process: While the planned Order-Assigned to Design Start time for ‘B’ orders shaves 5 days off from what is custom for ‘A’ orders, in practice that lead time is close to what it is for ‘A’ orders anyway. Some of that lost time in ‘B’ orders (‘lost’ meaning the difference between planned and actual) appears to be made up by less time spent on design: the planned value of these two combined is 7.3 d + 7.5 d = 14.8 d and the actual value 12.0 d + 3.5 d = 15.5 d. These values are a few days less than their counterparts for ‘A’ orders, 18.7 d and 17.5 d respectively.

Note that in both cases ‘A’ and ‘B’, the actual design time is less than the planned design time. It is the only task shown in Figure 10-9 for which this is the case. We speculate that the resources required to perform design are underloaded sufficiently so that they can accommodate ‘urgent’ demands without too much difficulty. Underloading means that a resource is not scheduled to work at 100% capacity at all times, but instead at 80% or 90% depending on the variability in work flow. Underloading is a management technique for creating reliability in work flow and throughput in systems that are subject to variability. Underloading should make it feasible to estimate durations more accurately, but the practice of padding schedules is deeply engrained.

Fast-track jobs create turbulence downstream: In each case ‘A’ and ‘B,’ orders with changes saw an escalation of Engineering-Release to Ship-Date, with actual values being nearly double that of planned values. Moreover, ‘B’ orders had an actual value that is significantly larger than ‘A’ orders. Provided that it is correct to assume that orders with changes are on the fast track, a question then is how to manage changes while not jeopardizing fabrication?

Normal delivery is more reliable; fast-track delivery is plagued by uncertainty: For ‘A’ orders, the planned overall average duration (from order assigned to ship date) is closer to the actual than for ‘B’ orders. This discrepancy is primarily due to the fact that orders with COs have a much longer actual average engineering release to ship date lead time (11.4w) than orders without COs (6.1w). This suggests that change orders adversely affect fabrication scheduling, thereby hampering its ability to deliver the product in a reasonable manner.

Schedules always slip: For all Butler orders (those with or without COs), actual ship dates exceed original and revised planned ship dates by several weeks, about 3 weeks for ‘A’ orders and about 5 weeks for ‘B’ orders. This suggests that Butler Plant's fabrication scheduling can be improved so that planned dates are less optimistic and closer to actual dates.

## Delivery Performance to Scheduled Commit Date

Of the 21 orders analyzed, only 17 had information relating to actual ship dates. Among these, only 4 were fulfilled (actual delivery) on or before the original planned ship date. Therefore, the Delivery Performance to Scheduled Commit Date ratio is a mere 4/17 or 23.5%. The actual ship date of these four orders coincided exactly with the original planned ship date, so that none of the 4 were shipped early.

The percentage of orders that were fulfilled within a week and three from the original planned ship date is 41.2% (7/17) and 47.1% (8/17), respectively. In order to better comprehend the reasons behind the poor estimation of original planned ship dates, Butler should compile the reasons for failure and a conduct a root cause analysis.

# LESSONS LEARNED

Several lessons are learned from analyzing the Butler case and its desire to succeed:

- Elasticity in production capacities: Since frame production is usually the fabrication constraint at the Visalia plant, Butler always runs frame production (primary steel fabrication and its associated connections) at this plant 3 shifts per day, 5 days per week. The other materials typically do not run at capacity. These typically run on 1 or 2 shifts per day, depending on the component produced and demand for that component. This elasticity in the production capacity (by controlling the number of shifts used per day) to accommodate market variability has helped Butler maintain competitive delivery schedules while mitigating costs of non-critical production activities.

- Modularization and its impact on the production process (supply chain): By categorizing designs according to degree of project customization, Butler was able to improve the efficiency of its design function and fine-tune it to take advantage of its fabrication capabilities.

- Serving customer needs – supplier design for constructability or mistake-proofing (poka-yoke): Butler spends considerable time and effort learning from its Builders and BUCON what the degree of constructability is of their products. The company invests heavily in research and development in order to make its products more appreciated by building erectors as well as owner-operators. For example, Butler worked with an upstream supplier to engineer a new kind of sealant (a putty-like material with tiny cubes in it) that a worker cannot compress too much during installation (doing so would squeeze the material out from the joint and thereby prevent sealing action). This putty material comes is rolled with layers separated in easily removable, non-tear plastic strips, and one side of the strip is precut lengthwise to allow for easy positioning of a screw through it.

- Gaining insight into product demand: In recent years, Butler has established a Corporate Alliance group that courts large owners, users of large Butler buildings. Because these owners have facilities around the country, sometimes even around the world, no Builder is in a position to serve them consistently. Butler’s Alliance group was formed exactly for that reason. In developing a close relationship with them, Butler also is gaining insight into upcoming demands for their products, which is of course extremely valuable from a production viewpoint.

- Standardization: Butler has been able to provide a relatively short made-to-order delivery time by standardizing products, automating large parts of the design process, maintaining approximately 3-month worth of inventories, and distributing production capabilities around the country so as to be close to delivery locations.

# CONCLUSIONS AND RECOMMENDATIONS

Although Butler is proactive about improving its processes, its application of lean production resides primarily at the plant level. By applying lean production principles across its internal functional divisions, Butler can realize additional improvements, in areas such as:

- Batching: The batching process from order-to-phase-to-manifest could be improved to facilitate flow. The design information may not be needed all at once (as Pronto demands now), given that only some information is needed to start production. For example, the primary structurals can be designed first and released into production while the design of secondaries is under way. By releasing the time-critical production of the primary steel members, the overall design and fabrication duration of the entire project may be reduced. Furthermore, primary structurals also are the members needed first in construction so this re-sequencing of work may also benefit further downstream operations. Butler should reconsider how projects are broken up in pieces (batches) that define the various units for design, document generation, fabrication, and shipping and streamline that process with work flow and the final unit of handoff to the contractor in mind,

- Transparency: Butler can improve transparency across its internal functions and across its supply chain in order to tighten the rules-of-thumb that are currently used to replenish inventories. For example, Butler can be clearer about what is needed when, so that when deadlines are missed, the impact on production is better understood. Butler can also make its production process more transparent to its construction customers (the Builders and BUCON) without necessarily giving away its competitive advantage. This way, it would perhaps be able to penalize its customers for late changes.

- Synchronization, One-Piece Flow, and Pull: Butler could further study the time its employees spend especially on soliciting and rectifying customer order data. This process presently appears to be extremely time consuming and subject to variability so that it takes away from Butler’s design and fabrication efficiency. A suggestion is for Butler to decouple order taking from design. Similarly, the permitting process appears to be extremely time consuming and subject to variability. This process should be decoupled from design (upstream) and fabrication (downstream). Butler should then work towards aiming for continuous flow in each of these four de-coupled production phases.

- Production Balancing: Butler’s design and fabrication processes were mapped using symbols that represent value-adding work as well as ‘holding’ positions (a.k.a., transfer points, queues, inventories, waiting lines, etc.) Each process step was defined in terms of its value-added time, setup time, and queue time. It appears as though the various production steps all progress at their own pace with relatively little consideration for the pace of other processes that are part of the same sequence or whose outputs merge at a later time. The production system as a whole, across design through fabrication, has not been balanced. This lack of balancing has many reasons, which have to do with variability and risk.

- Alliances: Butler currently has longer-term procurement agreements in place for structural steel. These were not investigated in the study, but they may be worth looking into by Butler to further improve SC performance.

- Horizontal Integration: Butler has bought other supplier firms (doors and window suppliers) but it is not clear to what extent these products or processes have been streamlined to integrate with Butler’s products and processes.

- Process Maps: Butler should further detail the process maps that have been created in the course of this research to identify additional opportunities for SC improvement from a total systems perspective.

- Array of Products Produced: Butler should reconsider what it is producing at each of its 6 fabrication plants. Presently, all plants can make all primary and secondary steel components, albeit in a limited set of colors (some plants offer a wider selection than others), but some cannot make trim components such as eaves, gutters, etc. Butler must therefore ship such components between plants. It is quite possible that the cost to invest in tools and equipment to make these components in small quantities is not prohibitive, and would offset the cost of inter-plant transportation. (The decision to ship between plants may be driven by Butler’s past investment in fully automated but expensive production facilities, whose costs must be offset by high volumes of production.)

# Acknowledgements

Many thanks are due to all people interviewed, for the time they spent and knowledge they shared with us. The authors are deeply indebted to J.C. Boyers, Operations Manager in Butler’s Corporate Alliance Team, for the wealth of information he has provided relating to Butler’s organization, and operations, and data for this case study. This research project would not have been possible without J.C.’s continued assistance.

The authors would particularly like to thank Greg Stolze, Butler Visalia’s Plant Manager, for sharing his knowledge and expertise regarding the operations and demands of Butler’s Visalia plant. The authors would also like to individually thank Alice Brown, Cathy Drennen, Keith Neill, Mark Nore, Anthony Portugal, and Chris Pursifull at Butler Visalia; Charles Milburn and Cliff Robertson at Butler’s Research Center in Kansas City; Brent Holt and John Tucker at Butler’s Kansas City Headquarters; Bill Johnsmeyer, Gary Dixon, Darrell Freeman, Darren Hiley, Jack Hott, Vivian Kieslich, Bob Knapp, Dan Mitchell, Doug Pettijohn, Kenny Strope, and Paul Wildschuetz at Butler Construction in Kansas City; and Ellis Daniels at Valley Steel Construction in Fresno for generously sharing their specialized knowledge and experience in the pre-engineered metal building industry.

This research was funded in part by a grant for task force PT 172 “Improving Construction Supply Chain Performance” from the Construction Industry Institute whose support is gratefully acknowledged. The opinions presented herein are those of the authors and not necessarily reflect those of the Construction Industry Institute.

# References

Akel, N.G., Boyers, J.C., Tommelein, I.D., Walsh, K.D., and Hershauer, J.C. (2001). "Considerations for Streamlining a Vertically Integrated Company: A Case Study." Ninth Annual Conference of the International Group for Lean Construction (IGLC-9), 6-8 August 2001, Singapore.

Arbulu, R.J., and Tommelein, I.D. (2002). “Value Stream Analysis of Construction Supply Chains: Case Study on Pipe Supports Used in Power Plants.” Tenth Annual Conference of the International Group for Lean Construction (IGLC-10), 6-8 August 2002, Brazil.

Brunt, D. (2000) “From Current State to Future State: Mapping the Steel to Component Supply Chain.” The International Journal of Logistics: Research and Applications, 3 (3) 259-271.

Elfving, J.A., and Tommelein, I.D., and Ballard, G. (2003). “An International Comparison of the Delivery Process of Power Distribution Equipment.” Eleventh Annual Conference of the International Group for Lean Construction (IGLC-11), 22-24 July 2003, Virginia.

Elfving, J.A., and Tommelein, I.D., and Ballard, G. (2002). “Reducing Lead Time for Electrical Switchgear.” Tenth Annual Conference of the International Group for Lean Construction (IGLC-10), 6-8 August 2002, Brazil.

Hopp, W.J., and Spearman, M.L. Factory Physics: Foundations of Manufacturing Management. Irwin/McGraw-Hill, Boston.

Jones, D. and Womack, J. (2002). Seeing the Whole – Mapping the Extended Value Stream. March, The Lean Enterprise Institute, Brookline, MA, 97 pages.

Lean (2002). Lean Construction Institute Glossary. http://www.leanconstruction.org. Visited April 20, 2002.

Rother, M. and Harris, R. (2001). Creating Continuous Flow – An Action Guide for Managers, Engineering, and Production Associates.. V. 1.0, June, The Lean Enterprise Institute, Brookline, MA, 104 pages.

Rother, M. and Shook, J. (1998). Learning to See: Value Stream Mapping to Add Value and Eliminate Muda. V. 1.1, October, The Lean Enterprise Institute, Brookline, MA, 106 pages.

SCOR (2000). Supply Chain Operations Reference (SCOR) Model, Supply Chain Council, Inc., Pittsburg, PA, Version 3.1, March 2000. www.supply-chain.org

Shoemaker, W.L. (1999). “Metal Building Systems: A New Look.” Civil Engineering, June, 69 (6) 56-59.

Simchi-Levi, D., Kaminsky, P., and Simchi-Levi., E. (2000) Designing and Managing the Supply Chain: Concepts, Strategies, and Case Studies. Boston, MA, McGraw Hill.

Supply Chain Operations Reference (SCOR) Model, Supply Chain Council, Inc., Pittsburg, PA, Version 3.1 March 2000. www.supply-chain.org

Tommelein, I.D., Walsh, K.D., and Hershauer, J.C. (2003). “Improving Capital Projects Supply Chain Performance.” Construction Industry Institute Research Report 172-11, May 2003, University of Texas at Austin.

# Footnotes

Ph.D. Student, P.E., Civil and Envir. Engrg. Department, 215 McLaughlin Hall, Univ. of California, Berkeley, CA 94720-1712, TEL/FAX 925/465-4655, nadia@astound.net

Professor, Civil and Envir. Engrg. Department, 215-A McLaughlin Hall, Univ. of California, Berkeley, CA 94720-1712, 510/643-8678, FAX 510/643-8919, tommelein@ce.berkeley.edu

Corporate Alliance Team Operations Manager, Butler Manufacturing Company, 700 Karnes Blvd. (64108) P.O. Box 419917, Kansas City, MO, 64141-0917, 816/968-3914, FAX: 816/968-4385, jcboyers@butlermfg.com

# Comments

Construction start data is not available. This would be interesting to measure.

From Visio File ButlerVisaliaStandardProjectDesignProcess_04_15_04.vsd

Note to Carlos: Are figure colors okay for printing and posting on the web?

From Table 2 Worksheet in ButlerOrderData_03_25_04..xls

From CE290N lecture notes on 2/24/04.

From Table 2 Worksheet in ButlerOrderData_04_14_04..xls

From CE290N lecture notes on 2/24/04 on value stream analysis and the pipe support case.

I went ahead and included a description of the components. I’m not sure if you want this info in this report.

From Visio File FabTimes_04_15_04.vsd

Nadia to do takeoff of actual building...incomplete.

For a description of the materials fabricated at Butler, you can either keep this paragraph or the following list of definitions. It’s up to you , Iris.

Need to check with Iris if this is calculated correctly. Based on definition in the PT172 manual, the critical time fence is construed to take place when fabrication begins. This calcs for the Plan Stability do not reflect this, as we didn’t have fabrication information of the Butler data.

From Visio File ButlerOrderCO_05_06_02.vsd

Nadia to obtain permission to list Butler and Valley Steel employees.

Porter’s book on Value Chains? Iris, I wasn’t able to get the book from the library last week. Also, I wasn’t able to get Hopp & Spearman’s books (2 copies) so that I could include Little’s Law as they were checked out. I did place a request for the books and just got a notice saying Hopp & Spearman’s book is on hold for me.

Other refs. On make vs. buy decisions?

# Text boxes

60’

100’

50 primaries

400 secondaries

10 brace rods

clips

ridge cap

connections

300-400    wall/roof panels