Simulation of buffering and batching practices IN THE interface detailing-fabrication-installation of HVAC ductwork

Thais da C.L. Alves and Iris D. Tommelein

# Abstract

Modeling the HVAC (Heating, Ventilating, and Air Conditioning) ductwork supply chain presents challenges at different stages given the nature of the product involved. Metal coils and sheets can be quantified in terms of length and pounds. However, when they are transformed in ducts and fittings, quantification becomes more complex. First, some sheet metal companies measure their throughput in terms of pound mass of sheet metal per time and not in units of fittings and ducts per time, regardless of the level of complexity to fabricate these parts. Second, fittings and ducts have some of their characteristics specified but not all of them; there is a quite high degree of customization for both products. This paper investigates the activities in the interface detailing-fabrication-installation of HVAC ductwork and uses the simulation software STROBOSCOPE to mimic the behavior and outputs of these activities as well as the interaction among them. The data used to develop this model comes from an ongoing study about HVAC subcontractors. The model specifically deals with variations in batches and buffers sizes and their impact on the system throughput, work in process, and cycle times. Analysis of the different scenarios studied provides insights as to how lean concepts can be used to trigger improvements in the interface investigated.

# KEY WORDS

Buffer, batch, sheet metal duct work, HVAC system, mechanical contractors, simulation

# Introduction

Research to date has indicated some concerns of the research community regarding the study of several aspects of buffers in construction. Previous studies addressed how buffers are or should be used in different types of construction projects (Howell and Ballard 1996, Horman and Kenley 1998); how buffers are generated in production systems (Tommelein 1998, Tommelein et al. 1999, Tommelein and Weissenberger 1999); and how capacity buffers can be used to reduce waste and improve project performance (Horman 2001, Sakamoto et al. 2002).

The AEC industry uses several practices to keep workers, machinery, and equipment busy at all times. This industry is obsessed by the idea that all resources should be kept busy, even when they are performing tasks that are not directly needed to advance a project. In order to keep people working at all times large buffers may be found in construction. The use of buffers in production systems stems from the desire to optimize labor and machine utilization as well as from the acknowledgement that uncertainties exist in the supply chain (Tommelein and Weissenberger 1999).

The need to protect production in construction against variations in the supply chain also stems from several obstacles related to uncertainty. Some of them are the lack of a single authority that can ensure or improve the rate of system output; the interactions between subcycles, which make it difficult to predict the output rates and the methods used to accomplish the tasks (Howell et al. 1993); and the difficulty to control one’s own pace. “Large buffers reduce the need for reliable planning as they allow some work to get done despite uncertain flows. Large buffers allow flexibility and mask the extent of uncertainty because current planning systems fail to control work flow (Howell and Ballard 1996, p. 41).” Therefore, the definition of buffer profiles, i.e., type, location, and size, and their proper allocation in a supply chain is an important aspect for revealing system’s inefficiencies and ultimately to achieving continuous flow.

The simulation model presented on this paper is part of an ongoing research, which aims at studying buffering practices in the construction industry. Unveiling the rationale behind the definition of buffers by construction companies and studying their impact on construction supply chains is one of the main goals of this research.

On this paper, the authors simulate the behavior of the supply chain for HVAC sheet metal ducts. Specifically, the detailing, fabrication, and installation of sheet metal ducts and fittings for HVAC systems by mechanical contractors are discussed. Mechanical contractors have multiple capabilities such as design-fabrication-installation of HVAC, plumbing, piping, and installation of related equipment such as chillers, fans, boilers, and pumps. Design-build mechanical contractors play an important role in the supply chain for HVAC systems because one single supplier may be in charge of almost the entire life cycle of the HVAC system. Once the raw material is under the mechanical contractor’s governance, design, fabrication, installation, and maintenance can be all performed by a single subcontractor (Miles 2000). This supply chain integration of fabrication and construction is not common in the construction industry. In the structural steel industry, for instance, design and construction may be performed by the same or different companies, but fabrication is usually done by a third-party supplier (Tommelein and Weissenberger 1999).

The mechanical contractor work represented in the supply chain for HVAC sheet metal ducts and fittings deals only with the production of ducts and fittings. Its scope of work comprises the detailing of ducts on site and at the fabrication shop, the fabrication of ducts on an in-house facility, and the installation of ducts and fittings on site. Another entity not explicitly modeled is the work of other trades that precede the installation of HVAC ducts and fittings, this is briefly mentioned in the model as an entity that generates work spaces on a regular basis so that the HVAC installers can perform their work. In the model discussed on this paper, buffers and batches are explicitly modeled and their impact on the overall supply chain is discussed.

# Types of Buffers

A production system has to be buffered against variability in order to avoid loss of throughput, wasted capacity, inflated cycle times, larger inventory levels, long lead times, and poor customer service (Hopp and Spearman 2000). “While there is no question that variability will degrade performance, we have a choice of how it will do so. Different strategies for coping with variability make sense in different business environments.” (Hopp and Spearman 2000, p. 295). According to Hopp and Spearman (2000, p.295), there are three types of buffers to protect a production system against variability, namely inventory, capacity, and time.

Physical inventories may be categorized according to their position and purpose in a value stream. “Raw materials, work-in-process, and finished goods are terms used to describe the position of the inventory within the production process. Buffer stocks, safety stocks, and shipping stocks are terms used to describe the purpose of the inventory” (The Lean Enterprise Institute 2003).

In construction, considerations about the environment, i.e., site access and conditions, play a major role in defining how much capacity should be allocated to a certain project. Some units to express capacity may include number of available hours of resources (Buffa 1969), space required to perform operations (Tommelein and Zouein 1993), safety and risk levels related to performing operations (Bea 2002), e.g. OSHA exposure levels to chemicals or dust. The next relevant point to evaluate capacity strategies is the make or buy decision. If a mechanical contractor decides to outsource fabrication of the parts it is able to fabricate, it may be giving up part of the power it has in terms of process control and/or part of its profits. Conversely, outsourcing may be freeing up capital that would otherwise be committed to production.

Time buffers are used in project management. Goldratt (1997) suggests that the estimates for a project usually have extra time embedded in them to deal with variations. The fact is that this extra time is always used by people because of Parkinson’s Law, which says that a task will take as long as the time allotted for it to be done. Goldratt stresses that the use of time buffers is wrong: instead of being used to deal with uncertainties they are always used as a part of the time to perform a task. In Critical Chain Project Management (Goldratt 1997), time buffers are used to manage schedules. They are sized according to the length of the task chain in the project and the uncertainty involved in each of the tasks of the chain. Depending on how much of the time buffer is actually used, action should be taken. Also, the concept of float in the Critical Path Method may be seen as some sort of time buffer. It provides flexibility to define the start dates for activities, without delaying project completion.

# the supply chain of sheet metal Ducts and fittings

The lack of work structuring regarding the way design tasks and construction tasks develop and the use of ductwork documents that are not value-adding, because they are not a good representation of the reality crews encounter on the field, are among the problems identified by Milles and Ballard (2002) in the interface between mechanical design and construction.

These problems contribute for the difficulties project managers have in scheduling the mechanical crew’s work and the supply of ducts and other parts from fabrication shops. Therefore, managers may plan for buffers on the interfaces between tasks on this supply chain to decouple operations (Howell et al. 1993), or allow piles of inventory to accumulate between different stages in the supply chain as a result of variations and mismatches in the flow of inputs and outputs (Alves and Tommelein 2003). One way to reduce or eliminate buffers in this supply chain is to implement a pull system. In this system, site installation pulls sheet metal parts when all the other pre-requisites for installation have been taken care of. This practice is illustrated on the simulation model discussed on this paper.

The type of work developed by mechanical contractors, which design, fabricate, and install sheet metal ducts and fittings for HVAC systems, is a service type of work. This characteristic determines the way the supply chain for this product is set up. Mechanical contractors provide a service and produce a product. The products fabricated, ducts and fittings, can be stocked up, but only to a degree because ducts are a made-to-order product and parts are usually large, which make it difficult for contractors to store them. The services, design and installation cannot be stocked up. Parts can be assembled and tested separately but the entire work must be put together only at its final location. Moreover, the customer has a high level of input in the process; the design is custom-made according to customer’s specifications and often allowed to change even during the construction phase to accommodate customer’s needs. A service characteristic that fits the mechanical contractors’ work follows:

“Frequently, the consumption of a service is nearly simultaneous with its production. Services cannot be inventoried for use later on. This fact has some serious implications for capacity choice and capacity management in a service business. The site, size, and layout choices for service industries are critical. (…) Demand irregularities place a tremendous burden on a service operation to be flexible. They also force services to manage their demand via prices or the kinds of services offered.” (Schmenner 1993, p. 16)

Based on the characteristics presented, one can advocate that the pull system is adequate to the supply chain investigated because its products, to a large extent, cannot be kept on inventory. Therefore, the detailing and fabrication of ducts should be triggered only when the level of uncertainty regarding the types of parts needed is minimal, the pre-requisite tasks are done, and when these parts can arrive on site and installation can proceed almost immediately. It is worth noting that the use of a pull mechanism does not preclude the use of buffers in the system. Different production rates, levels of uncertainty, and requirements for activities require that buffers be located between these to assure a continuous flow of work. However, sizing the buffers between these activities is a challenge because participants on a supply chain may not be willing to share information about their production capabilities or may not be able to see the impact their actions have throughout the entire supply chain, e.g. the illustration of the beer game by Senge (1994).

# Simulation model to mimic Batch and Buffer Allocation throughout the HVAC Production System

Part of the waste and the problems that plague the construction industry are the result of local optimization initiatives performed by individual firms (Vrijhoef and Koskela 1999). This is aggravated by the lack of communication and transparency among supply chain participants in construction (Tommelein 1998). Therefore, any effort that aims at increasing transparency and the understanding of how systems work in the AEC industry are welcomed. According to Tommelein (1998, p. 287-288), “(p)articipants who can ‘see’ the other’s needs, can better plan to accommodate them.” Therefore, anticipating the main problems that may surround a project and properly preparing the production system to deal with them is likely to improve a firm’s competitiveness. This happens due to a likely reduction on a firm’s operating expenses and the increase on its flexibility to quickly respond to changes in the environment.

The software used to model and simulate the supply chain for HVAC ducts and fittings is the STROBOSCOPE system, which “is a programming language that represents resources as objects that have assignable, persistent, and dynamic properties; and that can actively and dynamically take into consideration the state of the simulated process” (Martinez 1996, p. 406).

## Representation of the HVAC Supply Chain Using STROBOSCOPE Symbols

### Assumptions and limitations of the model

In order to develop the simulation model for this paper, the authors have made some simplifications and assumed some parameters based partially on interviews with mechanical contractors, and partially on the authors own understanding of the activities represented. Durations were mainly defined based on conversations with mechanical contractors’ personnel and are represented in days. Each work day has 8 hours and there are no representation of breaks, weekends, and holidays. The size of buffers and the relationships between them were defined based on the authors’ assumptions about the different activities represented.

All parts are assumed to be equal and are detailed, fabricated, and installed on a first-in-first-out (FIFO) basis. The number of resources necessary to detail, fabricate, and install parts is the same for all parts. The model also assumes that there is a relationship between buffers in the system and the activities they precede. Figure 1 shows the activities (rectangles) and the buffers (triangles) between each of them. BufSize is a variable defined in the model, which assumes different values and influences the amount of work-in-process and throughput of the system as well as the lead time to install a defined number of ducts.

Figure 1: Minimum buffer sizes between activities.

For instance, between PrepSpace and InstallHangers there is a buffer whose size is equal to the ‘BufSize’ defined in the model. That means that at least an amount equal to BufSize has to be available so that Install Hangers can start. Between Fabricate and ShipDucts, the buffer is five times the size of the ‘BufSize’. This means that the shipping activity can only start after ‘5*BufSize’ is available. The large buffer between these two activities is intended to deal with the fact that the shipping activity may have to be delayed until different parts required for a certain area are put together in a single batch to be sent to the construction site on a single truck.

The sequence of activities required to detail, fabricate, and install sheet metal ducts and fittings was simplified. For instance, Bhattal (2002) developed a model that illustrates most of the activities required to fabricate a duct. However, in the simulation model presented herein, fabrication is represented as a single activity that bundles all the steps needed to fabricate a duct.

Finally, it is assumed that the trucks used to ship ducts to the construction site can only transport at most 40 ducts per trip. Spaces, details, and ducts have a 1:1:1 relationship in the model, i.e. one space is used to produce one detail, which is used to fabricate one duct. The relationship between cut sheets and ducts is 1:5, i.e. one cut sheet has five ducts detailed on it.

### Simulation model

The simulation model for the supply chain of sheet metal ducts for HVAC systems is shown in Figure 2. Durations, amount of resources, relationships between activities, and some commands used in the STROBOSCOPE source code are presented in Figure 2. The model has five main subsystems namely Site Work – Preparation of Space, Site Detailing – Faxing Cut Sheets, Shop Detailing, Fabrication – Shipping of Ducts, and Installation.

The simulation starts when the activity PrepSpace GENERATEs 10 AReadySpace, which are work areas ready for the mechanical crews to start working. Every time this activity happens it releases to the subsequent activity 10 AReadySpace, this number is not a function of the BufSize variable. Crews that ‘InstallHangers’ wait until at least a BufSize of AReadySpace is available to start working, and when their work is over, they release a BufSize of ADuctPath to Detailing. InstallHangers is the activity that triggers the order for ducts. Once hangers are installed, the positions of ducts and their characteristics are defined and the site Detailer can prepare the cut sheets that represent orders, and fax them to the fabrication shop. Five ducts are detailed on each cut sheet, which is faxed to the fabrication shop to be CadDetail(ed).

The Shop Detailer waits until 0.2*BufSize ACutSheet(s) accumulates before they can be detailed on CAD. CadDetail GENERATES a BufSize of ADetail3D, which is sent directly to the Fabricate activity. After ducts are fabricated, they are sent to ShipBatch, which consolidates a number of ducts equal to 5*BufSize before they are released to the ReadyShip queue. ShipDucts draws ducts from ReadyShip and uses two trucks that can only transport 40 ducts per trip per truck. Finally, Installation starts only after 2*BufSize of AReadyDuct(s) have accumulated on DuctSite and it GENERATES the same number of ducts installed, which are sent to the queue DuctInstalled, and represent the final output of the modeled system.

Figure 2: Simulation model for the HVAC Sheet Metal supply chain (Detailing – Fabrication - Installation).

# Analysis of Results

In order to evaluate the impact the assigned buffers have on the system modeled, the authors used different values for BufSize, i.e. 20, 50, 100, and analyzed the accumulated number of units throughout time (days) received by queues that succeed specific activities in the model. Results represent the output for the installation of 500 ducts on single runs. The activities and queues analyzed are shown in Table 1.

Table 1: Activities and queues analyzed

| Activity | Queue |
| --- | --- |
| InstallHangers | DuctPath |
| Detailing | CutSheets1 |
| CadDetail | Ncs |
| Fabricate | ReadyShip |
| ShipDucts | DuctSite |
| Installation | DuctInstalled |

Figure 3 shows the results for a BufValue equal to 20 units. In this figure, one can see most of the activities progressing in a smooth fashion. However, the DuctSite and DuctInstalled curves reveal the impact of two constraints: the maximum number of ducts transported by trucks (40 units) and the minimum number of ducts necessary to trigger the Installation activity. The combination of these two constraints and the batching activity, which occurs on ShipBatch, result on a curve that progresses on steps, and delays the final installation of ducts, which ends around day 35.

Figure 3: Units produced vs. time, for selected activities in the model, with BufSize = 20 units

Figure 4 shows the results for a BufSize equal to 50. The accumulated number of units on each queue again shows a smooth progression for the first four queues evaluated in the model namely DuctPath, CutSheets1, Ncs, and Ready Ship. However, the impact of larger buffers required throughout the system and the impact of the batching activity amplified the difference between the curves. Note that in two occasions, DuctSite and DuctInstalled had to wait for more than 10 days to receive the next shipment of ducts and the next batch of ducts installed, respectively. The last batch of ducts is installed around day 40.

Figure 4: Units produced vs. time, for selected activities in the model, with BufSize = 50 units

Figure 5 presents the results for a BufSize of 100. DuctPath, CutSheets1, and Ncs accumulated units progress in a smooth fashion, starting some time around day 7. The queues ReadyShip, DuctSite, and DuctInstalled started receiving ducts more than 25 days later, around day 35 because the effect of batching in ShipBatch and the reduced capacity of trucks to transport ducts to the site. On time 35, we observe that 500 ducts were available in ReadyShip to be shipped to the construction site, but trucks can only transport 40 ducts. Therefore, the contents of DuctSite grows in a steep fashion some time between time 35 and 40. Finally, the installation of ducts starts only after a buffer of 200 ducts is available, after day 35 and the installation of the 500 ducts ends around day 60.

Figure 5: Units produced vs. time, for selected activities in the model, with BufSize = 100 units

In the analysis of figures 3 to 5, one can see differences related to the way activities progress over time given the system’s constraints shown on Figure 1 and in the model on Figure 2. Another effect of the variation on the BufSize variable is the time it takes for the first group of ducts from the time ADuctPath is generated to the time ADuctInstalled enters the DuctInstalled queue. Table 2 shows the time the first and the last batches of each product, in each of the queues evaluated, was created for different values of BufSize.

Table 2: Simulation time and units produced for different values of the variable BufSize.

|  | BufSize = 20 | BufSize = 50 | BufSize = 100 |
| --- | --- | --- | --- |
| Event | Product | SimTime (days) | Units | SimTime (days) | Units | SimTime (days) | Units |
| First | Path | 2 | 20 | 2.99 | 50 | 8.34 | 100 |
| Last | Path | 32.27 | 600 | 37.68 | 750 | 51.43 | 1000 |
| First | Detail | 2.33 | 4 | 4.13 | 10 | 9.21 | 20 |
| Last | Detail | 32.6 | 120 | 38.07 | 150 | 52.97 | 200 |
| First | CAD detail | 2.59 | 20 | 4.71 | 50 | 10.22 | 100 |
| Last | CAD detail | 32.82 | 600 | 38.46 | 750 | 53.9 | 1000 |
| First | Fabricated duct | 7.02 | 100 | 14.23 | 250 | 35.33 | 500 |
| Last | Fabricated duct | 33.3 | 600 | 40.11 | 750 | 57.95 | 1000 |
| First | Shipped duct | 7.24 | 40 | 14.49 | 40 | 35.42 | 40 |
| Last | Shipped duct | 33.48 | 520 | 40.29 | 520 | 59.36 | 1000 |
| First | Installed duct | 7.51 | 40 | 15.32 | 100 | 37.17 | 200 |
| Last | Installed duct | 33.74 | 520* | 41.04 | 500* | 59.37 | 600* |

*Final numbers for the last batch of installed ducts differ because the model collects output data according to the variable BufSize and its impact on the system’s activities, and because of the termination condition for the simulation. The simulation runs until the activity Installation has finished and delivered a number of ducts that is equal or greater than 500, given the constraints on buffers, batches and outputs assumed.

Table 2 reveals that the time the first batch of 20 units of path, for BufSize = 20, took to become an installed duct was about 5.5 days. In other words, the first 20 ducts were ordered on day 2 and were installed on site on day 7.5, resulting on a lead time of 5.5 days. In the second scenario when BufSize = 50, at time 2.99 the first 50 ducts were ordered, i.e. 50 paths generated meaning that the site was ready to receive 50 ducts. The same 50 ducts ordered on time 2.99 were installed more than 10 days later, on time 15.32. For BufSize = 100 the lead time increases to 50 days. The first 100 ducts were ordered on time 8.34 and installed on time 59.37.

The influence of the batching after the ShipBatch consolidator is illustrated on Table 2 (gray lines) by the difference between the time the first batch of CAD detail is prepared and the time the first group of fabricated ducts is available to be shipped to the site. The higher the BufSize value the longer it takes for the batch to be assembled and released to the next activity. Finally, the times it took for the model to install 500 ducts grows as the BufSize variable grows. This is illustrated on the last line of Table 2.

# Conclusions

The model presented reveals the interactions between stakeholders and activities in the supply chain investigated and how the definition of buffers and batch sizes impact system output and lead time. In order to refine the results presented, the authors plan to collect more realistic data on the size of buffers required for each activity to start as well as on the durations of activities.

The authors did not investigate the effects of allocation of capacity and time buffers on this model. The different values assumed by the variable BufSize alter the physical inventory buffers, and the production rates to reflect an increase on the number of units turned out by each activity. The study of the allocation of different buffers and their impact on a supply chain is also part of the scope of work to be tackled by the authors on the long run.

Finally, one can see the increase in BufSize in this supply chain as an increase on buffers to deal with the level of uncertainty participants face on their work as part of a supply chain. Other things being equal, e.g. ratio of buffers between activities, overall constraints of the system, when participants need more input to make their crews available to start working, the lead time for a product increases and the system’s throughput falls.

# Acknowledgements

Thanks are due to Coordenação de Aperfeiçoamento de Pessoal de Nível Superior (CAPES) and the Brazilian Government for sponsoring the studies of Thais da C.L. Alves at the University of California at Berkeley. Any opinions, findings, conclusions, or recommendations expressed in this report are those of the authors and do not necessarily reflect the views of CAPES.

# References

Alves, T.C.L. and Tommelein, I.D. (2003) “Buffering and Batching Practices in the HVAC Industry.” Proc. Eleventh Annual Conference of the International Group for

Bea, R. (2002) Human and Organizational Factors: Risk Assessment and Management of Engineered Systems. Reader for the CE – OE 290N at University of California at Berkeley, Copy Central: Berkeley, CA. 444pp.

Bhattal, N. (2002) Process Simulation for Fabrication of HVAC Rectangular Ductwork Fittings. Master of Engineering Report, Constr. Engrg. and Mgmt. Program, Civil and Envir. Engrg. Dept., Univ. of California, Berkeley, CA

Buffa, E.S. (1969) Modern Production Management. 3rd Edition. John Willey and Sons, Inc.: New York. 795pp

Goldratt, E.M. (1997) Critical Chain. The North River Press: Great Barrington, MA. 246pp.

Horman, M. and Kenley, R. (1998) “Process Dynamics: Identifying a Strategy for the Deployment of Buffers in Building Project.” International Journal of Logistics: Research and Applications, 1 (3), 221-237.

Horman, M.J., Messner, J.I., Riley, D.R., and Pulaski, M.H. (2003) “Using Buffers to Manage Production: A Case Study of the Pentagon Renovation Project.” Proc. Eleventh Annual Conference of the International Group for Lean Construction (IGLC-11), 22-24 July, Virginia Tech, held in Blacksburg, VA, USA.

Horman, M.J. (2001) “Modeling the Effects of Lean Capacity Strategies on Project Performance.” Proc. Ninth Annual Conference of the International Group for Lean Construction (IGLC-9), 6-8 August, held in Singapore.

Hopp, W.J. and Spearman, M.L. (2000) Factory Physics. Second Edition. McGraw-Hill International Editions, Boston, 698 pp. (First Edition 1996)

Howell, G.A. and Ballard, H.G. (1996) Managing uncertainty in the piping process. RR47-13, Construction Industry Institute, Univ. of Texas, Austin, TX, September, 103pp

Howell, G.A., Laufer, A., and Ballard, G. (1993) “Interaction between Sub-cycles: One Key to Improved Methods.” Journal of Construction Engineering and Management, ASCE, 119 (4) 714-728

Martinez, J.C. (1996). STROBOSCOPE: State and Resource Based Simulation of Construction Processes. Ph.D. Dissertation, Department of Civil and Environmental Engineering, University of Michigan, Ann Arbor, MI, 518 pp.

Miles, R.S. and Ballard G. (2002) “Problems in the Interface Between Mechanical Design and Construction: a Research Proposal.” J. of Construction Research, 3 (1) 83-95, World Scientific Publishing Company.

Miles, R.S. (2000) Managing Workflow from Detailing to Installation. 2nd Annual Lean Congress, Berkeley, CA, Lean Construction Institute, August 2000.

Sakamoto, M., Horman, M.J., and Thomas, H.R. (2002) “A Study of the Relationship between Buffers and Performance in Construction.” Proc. Tenth Annual Conference of the International Group for Lean Construction (IGLC-10), 6-8 August, held in Gramado, Brazil.

Schmenner, R.W. (1993) Production/Operations Management. Englewood Cliffs, N.J.: Prentice Hall, 825 pp.

Senge, P.M. (1994) The Fifth Discipline: the Art and Practice of the Learning Organization. New York, NY: Currency Doubleday, 424 pp.

The Lean Enterprise Institute (2003) Lean Lexicon: a Graphical Glossary for Lean Thinkers. Version 1.0, January 2003. The Lean Enterprise Institute: Brookline, MA. 98pp.

Tommelein, I.D. (1998) “Pull-driven Scheduling for Pipe-spool Installation: Simulation of a Lean Construction Technique.” ASCE, Journal of Construction Engineering and Management, 124 (4) 279-288

Tommelein, I.D., Riley, D.R., and Howell, G.A. (1999) “Parade Game: Impact on Work Flow Variability on Trade Performance.” ASCE, Journal of Construction Engineering and Management, ASCE, 125 (5) 304-310

Tommelein, I.D. and Weissenberger, M. (1999). "More Just-in-Time: Location of Buffers in Structural Steel Supply and Construction Processes." in Tommelein, I.D. (editor), Proc. Seventh Annual Conference of the International Group for Lean Construction (IGLC-7), 26-28 July, held in Berkeley, CA, USA, 109-120.

Tommelein, I.D. and Zouein, P.P. (1993). "Interactive Dynamic Layout Planning." ASCE, Journal of Construction Engineering and Management, 119 (2) 266-287.

Vrijhoef, R. and Koskela, L. (1999) “Roles of Supply Chain Management in Construction.” in Tommelein, I.D. (editor), Proc. Seventh Annual Conference of the International Group for Lean Construction (IGLC-7), 26-28 July, held in Berkeley, CA, USA, 109-120.

# Footnotes

Ph.D. candidate, Engineering and Project Management Program, Department of Civil and Environmental Engineering, University of California at Berkeley, thaiscla@berkeley.edu

Professor, Engineering and Project Management Program, Department of Civil and Environmental Engineering, 215-A McLaughlin Hall, University of California, Berkeley, CA 94720-1712, 510/643-8678, FAX 510/643-8919, tommelein@ce.berkeley.edu